## ReadMe
CHECKPOINT — Scrum Development Plan (Planner Import Workbook)
Deadline: September 23, 2026 (Wednesday) ¦ Plan revised: September 3, 2026 (Thursday)
System: a live bus arrival tracker that locates buses from conductor checkpoint confirmations, with no GPS hardware on any vehicle.
Stack: MongoDB, Express, React (Vite), Node. Deployed as a single service with the API serving the built client.
SPRINT STATUS
Sprints 0, 1, 2 and 3 are COMPLETE. Their tasks are recorded here with a Status of Done and are evidenced by the repository history and the passing test suite.
Sprints 0, 1, 2 and 3 are COMPLETE. Sprint 3 is evidenced by the repository history and the passing test suite (182 server tests, 18 client tests). Sprints 4, 5 and Finalization run to the September 23 deadline.
HOW TO USE THIS WORKBOOK
1. Open the 'All_Planner_Tasks' tab. Each row is one Microsoft Planner task.
2. In Planner: create one Bucket per unique value in the 'Bucket (Planner)' column (format: 'Sprint N - Bucket Name').
3. Create a task per row using the Task Name, and paste the Description into the task’s Notes field.
4. Split the 'Checklist Items' cell on line breaks into individual Planner checklist items.
5. Set Start Date / Due Date, Priority, and Assigned To (role — assign to a real teammate) from the matching columns.
6. Mark every row whose Status is 'Done' as completed in Planner once imported.
7. For bulk import, use Power Automate ('When a new row is added' + 'Create a task' + 'Add a checklist item to a task'), or copy and paste manually for a team of this size.
OTHER TABS
Product_Backlog — the master backlog of user stories with priority, points and dependencies.
Testing_Checklist / Documentation_Checklist / Deployment_Checklist — master checklists referenced by the Planner tasks.
Risk_Register — project risks and how each is being handled.
Coverage_Audit — confirms every feature area and lifecycle activity appears somewhere in this plan, and names what is deliberately out of scope.
BEFORE YOU IMPORT
Assign every task to a real teammate. The Suggested Assignee Role column is a role, not a person.
Sprint 0-2 dates follow the repository history (September 1-3, 2026). If your project formally began earlier, extend Sprint 0 backwards to match.

## All_Planner_Tasks
Sprint | Sprint Dates | Bucket (Planner) | Task ID | Task Name | Priority | Description | Checklist Items | Related User Story | Dependencies | Suggested Assignee Role | Start Date | Due Date | Testing Required | Documentation Required | Definition of Done | Status
Sprint 0 — Setup & Architecture | Tue, Sep 1, 2026 (1 day) | Sprint 0 - Project Setup | T0.1 | Repository & Branching Strategy | Must | Stand up the Git repository and the conventions the team works under for the rest of the project. | - Create the GitHub repository with a README stub and .gitignore - Agree branch naming and commit message conventions - Give every member access and confirm each can push - Record the stack decision: MongoDB, Express, React (Vite), Node | Foundational | - | Scrum Master / Tech Lead | Sep 1 | Sep 1 | N/A (process task) | README.md stub | Repository exists, all members have access, and the first commit is pushed to main. | Done
Sprint 0 — Setup & Architecture | Tue, Sep 1, 2026 (1 day) | Sprint 0 - Project Setup | T0.2 | MongoDB Atlas & Environment Configuration | Must | Provision the database and establish how secrets are handled, so no credential is ever committed. | - Create the MongoDB Atlas cluster and the CHECKPOINT database - Define the .env contract: MONGODB_URI, JWT_SECRET, PORT, TRAFFIC_API_KEY - Add .env to .gitignore and confirm no secret is tracked - Verify the server connects to Atlas from a clean checkout | Foundational | T0.1 | Backend Dev | Sep 1 | Sep 1 | Server boots and connects to Atlas on a clean clone | Setup guide: environment variables | A teammate can clone, add their own .env, and run the server against Atlas. | Done
Sprint 0 — Setup & Architecture | Tue, Sep 1, 2026 (1 day) | Sprint 0 - Project Setup | T0.3 | Frontend Tooling & Design System | Must | Set up the React client and adopt a single component vocabulary so screens look like one product. | - Scaffold the Vite + React application - Install and configure Tailwind and the shared UI components - Set the typeface and colour tokens, including light and dark handling - Confirm npm run dev and npm run build both succeed | Foundational | T0.1 | Frontend Dev | Sep 1 | Sep 1 | N/A (process task) | Coding standards section in README | A clean checkout runs the client and builds without warnings. | Done
Sprint 0 — Setup & Architecture | Tue, Sep 1, 2026 (1 day) | Sprint 0 - Architecture & Design | T0.4 | Data Model Design | Must | Design the collections the whole system rests on, and settle what each one owns. | - Define Checkpoint: name, type (station or landmark), terminal flag, location, area - Define Route: ordered checkpoints, each with its baseline minutes from the previous - Define Trip: a frozen copy of the route plan, taken at creation - Define CheckpointLog: the event stream that trip state is replayed from - Define Bus and User (admin / conductor) with the role boundary | Foundational — every epic depends on this | T0.2 | Backend Dev | Sep 1 | Sep 1 | N/A here (covered by engine tests in Sprint 1) | Database / schema document | The schema is written down, reviewed by the team, and the reason a trip freezes its plan is recorded. | Done
Sprint 0 — Setup & Architecture | Tue, Sep 1, 2026 (1 day) | Sprint 0 - Architecture & Design | T0.5 | GPS-Free ETA Approach | Must | Settle the core research decision: how a bus is located without any GPS hardware. | - Establish that position comes only from conductor checkpoint confirmations - Define variance as elapsed time minus the cumulative baseline, measured from departure - Decide that variance is recomputed from departure every time, never accumulated - Decide that trip state is a pure replay of the log stream, so offline sync works - Record why no device location is read anywhere in the system | Foundational — the research contribution | T0.4 | Backend Dev / Researcher | Sep 1 | Sep 1 | N/A here (proven by the engine unit tests in Sprint 1) | ETA methodology document | The formula, its inputs, and the no-GPS constraint are written down and agreed. | Done
Sprint 0 — Setup & Architecture | Tue, Sep 1, 2026 (1 day) | Sprint 0 - Architecture & Design | T0.6 | System Architecture & Screen Map | Must | Diagram how the client, API, database and traffic provider fit together, and map the three audiences. | - Draw the architecture diagram (React client, Express API, MongoDB, traffic provider) - Decide single-service deployment: Express serves the built client, relative /api, no CORS - Map the three experiences: passenger (no account), conductor, admin - Sketch the primary screens for each | Foundational | T0.4 | Full-stack Dev / UI-UX | Sep 1 | Sep 1 | N/A | Architecture document, screen map | The diagram and screen map are reviewed and agreed by the team. | Done
Sprint 1 — Core Tracking System | Tue, Sep 1 – Wed, Sep 2, 2026 (2 days) | Sprint 1 - Authentication & Roles | T1.1 | Staff Sign-In & Role Separation | Must | One sign-in for all staff, with the account role deciding which product opens and what the API allows. | - Build the single staff sign-in screen - Issue a token on sign-in and attach the role to it - Route an admin to the admin console and a conductor to their trips - Enforce the role on every protected endpoint, not only in the UI - Allow the first admin to be created only while the system has no accounts | US-1.1, US-1.2, US-1.3 | T0.2, T0.3 | Full-stack Dev | Sep 1 | Sep 2 | API tests: a conductor token is refused on admin routes and vice versa | Security / access model document | A conductor cannot reach any admin endpoint, proven by an automated test. | Done
Sprint 1 — Core Tracking System | Tue, Sep 1 – Wed, Sep 2, 2026 (2 days) | Sprint 1 - Admin Console | T1.2 | Checkpoint Management | Must | Let an operator record every place a bus actually stops, with a real position on the map. | - Create, edit and delete checkpoints - Distinguish a station (passengers board, gets a board) from a landmark (timing point only) - Mark official origin and destination terminals - Place each checkpoint on a map and store its coordinates - Search a place by name and drop its pin without leaving the page | US-2.1, US-2.2 | T1.1 | Frontend Dev + Backend Dev | Sep 1 | Sep 2 | API tests for create, edit and delete; manual check that a pin lands on the real road | Admin guide: managing checkpoints | An operator can add a real terminal, place it accurately, and see it on the public map. | Done
Sprint 1 — Core Tracking System | Tue, Sep 1 – Wed, Sep 2, 2026 (2 days) | Sprint 1 - Admin Console | T1.3 | Route Builder with Travel-Time Baselines | Must | Build a route as an ordered list of checkpoints, each with the time the leg normally takes. | - Add checkpoints to a route in order and reorder them - Record the baseline minutes for each leg from the previous checkpoint - Force the origin baseline to zero - Support routes that share a trunk and then diverge - Guide a first-time operator through creating their first route | US-2.3, US-2.4 | T1.2 | Frontend Dev + Backend Dev | Sep 1 | Sep 2 | API tests for route creation and baseline validation | Admin guide: building a route | A complete route with realistic baselines can be created and is visible to passengers. | Done
Sprint 1 — Core Tracking System | Tue, Sep 1 – Wed, Sep 2, 2026 (2 days) | Sprint 1 - Admin Console | T1.4 | Fleet & Conductor Registry | Must | Register the buses and the conductors who will report on them. | - Create, edit and deactivate buses (plate number, operator name) - Create conductor accounts with credentials issued by the admin - Create and remove other admin accounts, refusing removal of the last one - List all three from the admin console | US-3.1, US-3.2 | T1.1 | Frontend Dev + Backend Dev | Sep 1 | Sep 2 | API tests for each CRUD path; test that the last admin cannot be deleted | Admin guide: fleet and staff | An admin can register a bus and a conductor, and the conductor can sign in. | Done
Sprint 1 — Core Tracking System | Tue, Sep 1 – Wed, Sep 2, 2026 (2 days) | Sprint 1 - Admin Console | T1.5 | Trip Scheduling with a Frozen Plan | Must | Schedule a bus and conductor against a route, and freeze the route plan onto that trip. | - Create a trip from a route, bus, conductor and scheduled departure - Copy the route checkpoints and baselines onto the trip at creation - Confirm that editing the route afterwards does not change a running trip - List, edit and cancel trips | US-3.3, US-3.4 | T1.3, T1.4 | Backend Dev | Sep 1 | Sep 2 | API test: edit a route mid-trip and assert the running trip is unchanged | Database / schema document: why the plan is frozen | A trip carries its own plan, and a later route edit provably cannot rewrite its history. | Done
Sprint 1 — Core Tracking System | Tue, Sep 1 – Wed, Sep 2, 2026 (2 days) | Sprint 1 - ETA Engine | T1.6 | Checkpoint-Based ETA Engine | Must | The core of the research: derive how far ahead or behind a bus is, and project every remaining stop. | - Replay the log stream in reportedAt order to derive trip state - Recompute variance from departure on every confirmation, never accumulate it - Project every remaining checkpoint from the current variance - Handle a skipped checkpoint without corrupting the arithmetic - Derive staleness on read, scaled to the segment baseline, and never store it - Keep the whole engine free of database, framework and clock dependencies | US-4.1, US-4.2, US-4.3 | T0.5, T1.5 | Backend Dev | Sep 1 | Sep 2 | Unit tests covering variance, re-projection, skipped checkpoints, out-of-order replay and staleness | ETA methodology document | The engine is a pure function, fully unit tested, and produces correct times for a full trip. | Done
Sprint 1 — Core Tracking System | Tue, Sep 1 – Wed, Sep 2, 2026 (2 days) | Sprint 1 - Conductor | T1.7 | Conductor Trip Screen & Checkpoint Reporting | Must | Give the conductor one screen and as few taps as the job allows, with no room for ambiguity. | - List the conductor’s own trips and open one - One prominent action: confirm the next checkpoint - Separate reaching a stop from leaving it, so a waiting passenger knows which - Report a delay, or a checkpoint passed without tapping - Allow a mistaken tap to be taken back within five minutes - Refuse any action on a trip not assigned to that conductor | US-5.1, US-5.2, US-5.3 | T1.6 | Frontend Dev | Sep 1 | Sep 2 | API test that a conductor cannot log against another conductor’s trip; undo window test | Conductor guide | A conductor can run a trip end to end from departure to arrival using only this screen. | Done
Sprint 1 — Core Tracking System | Tue, Sep 1 – Wed, Sep 2, 2026 (2 days) | Sprint 1 - Passenger | T1.8 | Public Arrivals Board | Must | The passenger-facing answer: every bus heading to a stop, soonest first, with no account needed. | - List every bus inbound to a station, soonest first - Show the bus plate prominently enough to pick it out at a curb - Show where the bus is: standing at a stop, or on the road between two - Show departures, arrivals and buses that have just got in - Mark a bus that has stopped reporting rather than showing a confident time - Require no sign-in anywhere on this path | US-6.1, US-6.2, US-6.3 | T1.6 | Frontend Dev | Sep 1 | Sep 2 | API test that the public board needs no token; board content test | None yet (folded into the user guide later) | A passenger can open a station and see accurate live arrival times without an account. | Done
Sprint 1 — Core Tracking System | Tue, Sep 1 – Wed, Sep 2, 2026 (2 days) | Sprint 1 - Passenger | T1.9 | Trip Detail & Route Timeline | Should | Let a passenger open one bus and see the whole journey, including which stops it has passed. | - Show the full checkpoint sequence with confirmed and projected times - Mark which stop the bus is at or heading into - Show how far ahead or behind the trip is running - Reach it from any row on the arrivals board | US-6.4 | T1.8 | Frontend Dev | Sep 1 | Sep 2 | Manual check against a trip in progress | None yet | Opening a bus from the board shows its full route and current position. | Done
Sprint 1 — Core Tracking System | Tue, Sep 1 – Wed, Sep 2, 2026 (2 days) | Sprint 1 - Testing & QA | T1.10 | Sprint 1 Testing | Must | Prove the foundation before building on it. | - Unit tests for the ETA engine across all log types - API integration tests against an in-memory database - Test the role boundary in both directions - Seed realistic demo data and verify a full trip end to end | All Sprint 1 stories | T1.6, T1.7, T1.8 | Whole team | Sep 1 | Sep 2 | Full suite green before Sprint 2 begins | Test plan, first test cases | Every Sprint 1 story has at least one automated test and the suite passes. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Stop Discovery | T2.1 | Map, Stop Search & Stops Near Me | Must | Three ways in, because passengers arrive knowing different things. | - Draw every placed checkpoint on a map, with routes as lines - Search a stop by name or city - Rank stops by distance from the passenger, within an honest distance cap - Say plainly when nothing is actually nearby instead of calling the closest one near - Never derive any bus position from a device location | US-7.1, US-7.2 | T1.8 | Frontend Dev | Sep 2 | Sep 3 | Manual test of the nearby radius; check the cap behaviour with no stop in range | User guide: finding your stop | A passenger can find their stop by name, by map, or by proximity. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Stop Discovery | T2.2 | Walking Directions to a Stop | Should | Get the passenger from where they are to the right curb. | - Offer walking directions from the passenger position to the chosen stop - Estimate walking minutes from the distance - Open directions in the device’s own map application | US-7.3 | T2.1 | Frontend Dev | Sep 2 | Sep 3 | Manual test on a phone | User guide | A passenger can tap through to walking directions for any stop. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Conductor | T2.3 | Seat Availability Reporting | Should | Tell waiting passengers whether it is worth waiting, without adding burden to the conductor. | - Three levels only: seats available, filling up, full - Ask for it at the moment it is knowable, when the bus is at a stop - Ride it along with a tap the conductor is already making - Clear the report when the bus reaches a new stop, since loading changes there - Always show where and when the report was made, never as a live measurement - Make a full bus visibly not worth waiting for | US-8.1, US-8.2 | T1.7 | Full-stack Dev | Sep 2 | Sep 3 | Engine test that load clears at a new stop; manual check of the attribution line | Conductor guide: reporting seats | A passenger can see how full an approaching bus was, and where that was judged. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Passenger | T2.4 | Terminal Wall Display | Could | A compact board for a screen mounted at a terminal, readable across a hall. | - Compact rows sized for distance reading - Automatic paging when there are more buses than fit - Derive the page from the clock so it cannot drift or stick - Show departures, arrivals and just-arrived buses | US-9.1 | T1.8 | Frontend Dev | Sep 2 | Sep 3 | Manual test with more trips than fit one page | None | A terminal screen cycles through all buses unattended. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Accuracy | T2.5 | Live Traffic Integration | Should | Correct the projection for what the road is actually doing, without spending API calls carelessly. | - Integrate a routing provider behind a swappable interface - Ask only about the one or two segments each bus is about to drive - Cache per segment so many buses on one route share a single lookup - Apply traffic only to the road ahead, never to a measured variance - Fall back to pure baselines when no provider is configured or the lookup fails | US-10.1 | T1.6 | Backend Dev | Sep 2 | Sep 3 | Engine test that traffic applies forward only; verify live values against the provider | Traffic provider document | A bus on a congested leg shows a later arrival, and the system still works with the provider switched off. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Admin Console | T2.6 | Automatic Travel-Time Measurement | Should | Stop asking an operator to guess how long a leg takes. | - Measure each leg with the routing provider when a route is being built - Use typical time rather than free-flow, so a bus is not permanently late - Add a dwell allowance at stops where passengers board - Return every value editable, since an operator knows things a routing engine does not - Report clearly which legs could not be measured and why | US-2.5 | T1.3, T2.5 | Backend Dev | Sep 2 | Sep 3 | API tests for the measure endpoint including the no-provider case | Admin guide: estimating travel times | An operator can build a route without guessing a single number, then adjust any of them. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Passenger | T2.7 | Destination-First Journey Search | Must | Answer the question a passenger actually has: how do I get to where I am going. | - Search by destination and return the buses that serve it - Treat any stop later on the trip as a destination, not only the final one - Return the boarding stop as the answer, with distance and walking time - Never offer a stop the bus has already passed; still offer one it is standing at - One result per bus, with other nearby stops on the same bus named on the row | US-11.1, US-11.2 | T1.8, T2.1 | Full-stack Dev | Sep 2 | Sep 3 | API tests: wrong-direction search, already-passed stops, distance filtering | User guide: planning a journey | A passenger can enter a destination and be told which bus to catch and where to stand. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Passenger | T2.8 | Countdown-Led Arrival Display | Should | Lead with the wait, not the clock, so nobody has to do arithmetic at a bus stop. | - Make the countdown the largest element and demote the clock time beneath it - Keep the clock time, since it is what a printed timetable is matched against - Never say a bus is due when it is overdue and unconfirmed — count up instead - Apply the same treatment on the board, the journey search and the terminal display | US-6.5 | T1.8 | Frontend Dev | Sep 2 | Sep 3 | Manual check of the overdue and stale cases | None | A passenger reads the wait directly, and an unconfirmed overdue bus never claims to be arriving. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Reliability | T2.9 | Offline Reporting Queue & Sync | Must | A tap must never be lost because the bus is somewhere without signal. | - Write every tap to device storage before attempting to send it - Stamp the time at the moment of the tap, not when it reaches the server - Give every tap an idempotency key so a retry cannot double-count a checkpoint - Send the queue automatically when the connection returns - Keep the trip screen usable while offline instead of replacing it with an error - Replay a batch that arrives out of order onto the correct state | US-12.1, US-12.2 | T1.7 | Frontend Dev + Backend Dev | Sep 2 | Sep 3 | API test draining a scrambled queue with a duplicate; browser test with the network cut | Conductor guide: working without signal | A tap made offline reaches the server with its original time once signal returns. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Accuracy | T2.10 | Traffic-Aware Delay Classification | Should | Stop flagging a bus as delayed for sitting in the traffic everyone else is sitting in. | - Record what the road was running at on the leg each tap closes - Keep schedule variance for the arrival time a passenger is told - Subtract road conditions to decide whether the bus is genuinely behind - Treat an unknown reading as excusing nothing - Keep showing the lateness even when the road explains it, and move only the blame | US-10.2 | T2.5 | Backend Dev | Sep 2 | Sep 3 | Engine tests for excused delay, genuine delay, and the no-data case | ETA methodology document | A bus in normal rush-hour traffic is not flagged, and a genuinely slow bus still is. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Quality | T2.11 | Mobile Layout Pass | Must | The conductor works on a phone and most passengers will too. | - Test every screen at phone width and fix anything running off it - Make the top bar fit without clipping navigation - Stack cramped two-column layouts on narrow screens - Fix overlays that render behind the map - Improve the accuracy of the passenger’s own location, and show its uncertainty | US-13.1 | T2.7 | Frontend Dev | Sep 2 | Sep 3 | Measured sweep at 375px for content past the viewport on every screen | None | No screen overflows or overlaps at phone width. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Quality | T2.12 | Optimistic Conductor Updates | Should | Move the conductor screen on the tap rather than on the server’s reply. | - Apply the obvious consequences of a tap immediately - Leave arrival times to the engine rather than guessing them on the device - Replace the local state with the server’s answer when it arrives - Confirm the two agree, so the screen never visibly jumps | US-5.4 | T2.9 | Frontend Dev | Sep 2 | Sep 3 | Browser test with the network delayed; unit tests for the local state transitions | None | The screen responds to a tap immediately even on a slow connection. | Done
Sprint 2 — Passenger Experience & Accuracy | Wed, Sep 2 – Thu, Sep 3, 2026 (2 days) | Sprint 2 - Testing & QA | T2.13 | Sprint 2 Testing | Must | Close the sprint with the suite green and the demo data realistic. | - Extend the engine tests to traffic, seats and delay classification - Add API tests for journey search and the measure endpoint - Add client tests for locating and optimistic updates - Re-seed and walk a full trip end to end | All Sprint 2 stories | T2.7, T2.9, T2.10 | Whole team | Sep 2 | Sep 3 | Full suite green before Sprint 3 begins | Test cases updated | Every Sprint 2 story is covered and the suite passes. | Done
Sprint 3 — Remaining Scope | Fri, Sep 4 – Thu, Sep 10, 2026 (7 days) | Sprint 3 - Scheduling | T3.1 | Recurring Schedule Automation | Must | The largest remaining operational gap: an operator currently types every single trip by hand. | - Define a recurring schedule: route, bus, conductor, departure time, days of the week - Generate trips automatically from each schedule for a rolling window - Let an operator edit or cancel one generated trip without breaking the pattern - Avoid creating a duplicate trip if generation runs twice - Show which trips came from a schedule and which were entered by hand | US-3.5 | T1.5 | Backend Dev + Frontend Dev | Sep 4 | Sep 10 | API tests for generation, duplicate protection and single-trip override | Admin guide: recurring schedules | A week of trips can be created from one schedule, and a single day can still be overridden. Done. Schedule model + scheduleService.js generate a rolling 7-day window; unique (schedule, service day) index prevents duplicates; one day can be cancelled, deleted or edited without breaking the pattern. Admin Trips page. | Done
Sprint 3 — Remaining Scope | Fri, Sep 4 – Thu, Sep 10, 2026 (7 days) | Sprint 3 - Reliability | T3.2 | Admin Correction of Trip Records | Must | A conductor has five minutes to take back a tap. Past that, only a dispatcher can put it right. | - Let an admin view the full log stream for a trip - Let an admin delete or correct a log outside the conductor undo window - Recompute the trip from its logs after any correction - Record who made the correction and when | US-12.3 | T1.5, T2.9 | Backend Dev | Sep 4 | Sep 10 | API tests for correction and recompute; test the audit trail is written | Admin guide: correcting a trip | A wrong checkpoint logged an hour ago can be fixed without touching the database directly. Done. Admin trip page shows the full log stream; add, correct or remove an update, each replaying the trip and writing a TripCorrection audit record. | Done
Sprint 3 — Remaining Scope | Fri, Sep 4 – Thu, Sep 10, 2026 (7 days) | Sprint 3 - Accuracy | T3.3 | Time-of-Day Travel-Time Baselines | Must | One number per leg cannot describe a road that takes 32 minutes at midnight and 39 at six in the evening. | - Extend the route model to hold a baseline per time band - Measure each band from the routing provider when building a route - Select the right band from the trip’s scheduled departure - Keep a single-value baseline working, so existing routes do not break - Confirm a rush-hour trip is no longer reported late for running normally | US-10.3 | T2.6, T2.10 | Backend Dev | Sep 4 | Sep 10 | Engine tests for band selection and the single-value fallback | ETA methodology document | A leg measured off-peak no longer causes every peak trip to read as late. Done. Routes carry per-band figures (MMDA rush hours); a trip picks each leg’s band from when it is due to drive it, with the single-value fallback intact. | Done
Sprint 3 — Remaining Scope | Fri, Sep 4 – Thu, Sep 10, 2026 (7 days) | Sprint 3 - Reliability | T3.4 | Offline Start-Up | Should | The queue only helps while the app is already open. A conductor who reloads with no signal currently gets nothing. | - Add a service worker that caches the application shell - Serve the conductor screen from cache when the network is unavailable - Show the last known trip when opening offline, clearly marked as such - Confirm a reload with no signal still reaches a usable screen | US-12.4 | T2.9 | Frontend Dev | Sep 4 | Sep 10 | Browser test: reload with the network disabled and confirm the app loads | Conductor guide: working without signal | The conductor app opens and accepts taps with no connection at all. Done. Service worker caches the app shell; staff screens keep their last answer per account; a network failure no longer signs anyone out. | Done
Sprint 3 — Remaining Scope | Fri, Sep 4 – Thu, Sep 10, 2026 (7 days) | Sprint 3 - Security | T3.5 | Sign-In Hardening | Should | Close the gaps named against authentication in the midterm assessment. | - Rate-limit sign-in attempts per account and per address - Add a password reset path for staff accounts - Require a password change on first sign-in for an admin-created account - Review token lifetime and renewal | US-1.4 | T1.1 | Backend Dev | Sep 4 | Sep 10 | API tests for rate limiting and the reset path | Security / access model document | Repeated failed sign-ins are throttled and a conductor can recover their own password. Done. Sign-in throttling per account and address, temporary passwords on admin-created accounts, one-time reset codes, sessions ended on password change. | Done
Sprint 3 — Remaining Scope | Fri, Sep 4 – Thu, Sep 10, 2026 (7 days) | Sprint 3 - Testing & QA | T3.6 | Sprint 3 Testing | Must | Close the sprint with everything new under test. | - Tests for schedule generation and duplicate protection - Tests for admin correction and recompute - Tests for time-of-day band selection - Full regression of the existing suite | All Sprint 3 stories | T3.1, T3.2, T3.3 | Whole team | Sep 4 | Sep 10 | Full suite green before Sprint 4 begins | Test cases updated | Every Sprint 3 story is covered and the suite passes. Done. 182 server tests and 18 client tests pass, covering schedule generation and duplicate protection, corrections and the audit trail, and band selection. | Done
Sprint 4 — Hardening & Testing | Fri, Sep 11 – Thu, Sep 17, 2026 (7 days) | Sprint 4 - Security & Access | T4.1 | Security Review | Must | Go looking for the ways in, rather than waiting to be shown them. | - Re-test the role boundary on every endpoint, in both directions - Confirm no passenger endpoint leaks staff or conductor identity - Check that no secret is present in the repository or the client bundle - Review error responses for information they should not carry - Confirm no device location is read or stored anywhere for a vehicle | US-1.5 | T3.5 | Backend Dev + Tech Lead | Sep 11 | Sep 17 | Security test pass with findings logged and closed | Security / access model document | Every finding is either fixed or explicitly accepted and written down. | Not started
Sprint 4 — Hardening & Testing | Fri, Sep 11 – Thu, Sep 17, 2026 (7 days) | Sprint 4 - Performance | T4.2 | Performance Pass | Should | The board is polled by many passengers at once and the conductor screen must feel instant. | - Measure board and trip response times under a realistic number of trips - Confirm passenger reads never trigger a traffic provider call - Review database indexes against the queries actually run - Reduce the client bundle where it is cheap to do so | US-13.2 | T4.1 | Full-stack Dev | Sep 11 | Sep 17 | Recorded timings before and after, on a realistic data set | Architecture document: performance notes | Board and trip reads are measurably fast with a full week of trips loaded. | Not started
Sprint 4 — Hardening & Testing | Fri, Sep 11 – Thu, Sep 17, 2026 (7 days) | Sprint 4 - Quality | T4.3 | Real-Device Testing | Must | Conductors work on their own phones, and an emulator does not prove much. | - Test the conductor flow on at least three real Android phones - Test the passenger board and journey search on real devices - Confirm the passenger location fix is accurate on a phone, not just a laptop - Test on a slow mobile connection, not office wifi - Log and fix anything that only appears on a real device | US-13.1 | T2.11 | Whole team | Sep 11 | Sep 17 | Device test matrix completed and findings closed | Test cases: device matrix | The conductor flow works on every device tested, on mobile data. | Not started
Sprint 4 — Hardening & Testing | Fri, Sep 11 – Thu, Sep 17, 2026 (7 days) | Sprint 4 - Reliability | T4.4 | Data Integrity & Recovery | Should | Know what happens when something goes wrong, before it does. | - Confirm a trip always recomputes correctly from its logs alone - Test recovery from an empty database: first admin, routes, trips - Document the backup approach for the database - Confirm a duplicate or late log can never corrupt a trip | US-12.5 | T3.2 | Backend Dev | Sep 11 | Sep 17 | Wipe-and-recover test performed and recorded | Deployment guide: backup and recovery | The system can be rebuilt from an empty database and a trip can be reconstructed from logs. | Not started
Sprint 4 — Hardening & Testing | Fri, Sep 11 – Thu, Sep 17, 2026 (7 days) | Sprint 4 - Testing & QA | T4.5 | Sprint 4 Testing & Bug Fixing | Must | Work through what the hardening sprint turned up. | - Triage every finding from T4.1 to T4.4 by severity - Fix everything blocking or major - Re-run the full suite after each fix - Record anything deliberately not fixed, with the reason | All Sprint 4 stories | T4.1, T4.3 | Whole team | Sep 11 | Sep 17 | Full suite green; findings list closed or explicitly deferred | Test report | No blocking or major defect remains open. | Not started
Sprint 5 — Stabilization | Fri, Sep 18 – Sun, Sep 20, 2026 (3 days) | Sprint 5 - Integration | T5.1 | Integration & Bug Fixing | Must | Everything together, on one build, behaving as one product. | - Walk every user journey end to end on a single build - Fix defects found, worst first - Confirm the three experiences agree on the same trip data | All | T4.5 | Whole team | Sep 18 | Sep 20 | End-to-end walkthrough recorded | Test report | Every journey completes without a workaround. | Not started
Sprint 5 — Stabilization | Fri, Sep 18 – Sun, Sep 20, 2026 (3 days) | Sprint 5 - Regression | T5.2 | Full Regression Test | Must | Prove that fixing late things did not break early ones. | - Re-run every automated test - Re-walk the core passenger, conductor and admin journeys manually - Re-check the role boundary after all changes | All | T5.1 | Whole team | Sep 18 | Sep 20 | Full regression pass recorded | Test report | The suite passes and the manual walkthrough is clean. | Not started
Sprint 5 — Stabilization | Fri, Sep 18 – Sun, Sep 20, 2026 (3 days) | Sprint 5 - Scope | T5.3 | Scope Checkpoint | Must | Decide honestly what ships and what is written up as future work. | - Review every Should and Could item still open - Cut anything that cannot be finished and tested in the time left - Move cut items into the future work section of the documentation - Confirm every Must item is complete | All | T5.2 | Scrum Master / whole team | Sep 18 | Sep 20 | N/A (decision task) | Documentation: future work section | The remaining plan is achievable in the days left, and cuts are written down. | Not started
Sprint 5 — Stabilization | Fri, Sep 18 – Sun, Sep 20, 2026 (3 days) | Sprint 5 - Cleanup | T5.4 | Final Code Cleanup | Must | Leave the codebase in the state it will be read in. | - Remove debug logging and dead code - Confirm no secret or credential is committed anywhere - Check comments still describe what the code now does - Confirm the build is clean with no warnings | All | T5.3 | Whole team | Sep 18 | Sep 20 | Regression re-run after cleanup | README final pass | The repository is clean, builds without warning, and holds no secret. | Not started
Finalization — Testing, Deployment & Defence | Mon, Sep 21 – Wed, Sep 23, 2026 (3 days) | Finalization - Testing | TF.1 | Full Scenario Test Pass | Must | Walk every role end to end against the finished build, following written scenarios rather than clicking around, so nothing is passed over because the person testing it already knows where it works. | - Write the test scenarios for passenger, conductor and operator - Walk each scenario against the finished build, step by step - Repeat the conductor scenario on a phone as well as a desktop - Record every point of confusion, not only outright failures - Fix what is fixable in the time left and log the rest | All | T5.4 | Whole team | Sep 21 | Sep 23 | Every written scenario walked and its result recorded | Test report: scenario results | Every scenario for all three roles has been walked against the finished build and the results written up. | Not started
Finalization — Testing, Deployment & Defence | Mon, Sep 21 – Wed, Sep 23, 2026 (3 days) | Finalization - Deployment | TF.2 | Production Deployment | Must | Get it running where it will be demonstrated from. | - Confirm production environment variables are set and correct - Deploy the built client and API as a single service - Run a production smoke test across all three roles - Confirm logs are reachable and the database is connected - Seed demo data and demo accounts on the production instance | All | TF.1 | Backend Dev / Tech Lead | Sep 21 | Sep 23 | Production smoke test passed | Deployment guide | The system is live at a public URL and every role works on it. | Not started
Finalization — Testing, Deployment & Defence | Mon, Sep 21 – Wed, Sep 23, 2026 (3 days) | Finalization - Documentation | TF.3 | Documentation Pack | Must | Finish the written work while the system is still fresh. | - Complete the README, setup and deployment guides - Complete the architecture and schema documents - Complete the ETA methodology document, including the formula and its limits - Complete the admin, conductor and passenger guides - Complete the test plan, test cases and test report | All | T5.3 | Whole team | Sep 21 | Sep 23 | Documentation checklist fully ticked | All documents listed in Documentation_Checklist | Every item on the documentation checklist exists and has been read by someone else. | Not started
Finalization — Testing, Deployment & Defence | Mon, Sep 21 – Wed, Sep 23, 2026 (3 days) | Finalization - Demo | TF.4 | Demo Data & Demo Script | Must | A demonstration that fails on stage undoes weeks of work. | - Seed realistic demo routes, buses, conductors and trips - Write the demo script scene by scene, with who does what - Decide what is shown and, deliberately, what is not - Dry-run the full demo at least twice, timed - Prepare a fallback if the network fails during the demo | All | TF.2 | Whole team | Sep 21 | Sep 23 | Two timed dry runs completed | Demo script | The demo has been run end to end twice without intervention. | Not started
Finalization — Testing, Deployment & Defence | Mon, Sep 21 – Wed, Sep 23, 2026 (3 days) | Finalization - Deployment | TF.5 | Final Regression After Cleanup | Must | The last chance to catch something the final changes broke. | - Re-run the full automated suite against the production build - Re-walk the demo script on the production instance - Confirm no debug artefact reached production | All | TF.2, TF.4 | Whole team | Sep 21 | Sep 23 | Final regression pass recorded | Test report final entry | The production instance passes the full suite and the demo script. | Not started
Finalization — Testing, Deployment & Defence | Mon, Sep 21 – Wed, Sep 23, 2026 (3 days) | Finalization - Defence | TF.6 | Defence Preparation | Must | Be ready for the questions, including the uncomfortable ones. | - Prepare the answer to how the ETA is calculated, with the formula - Prepare the answer to what happens between checkpoints - Prepare the honest account of the system’s limits and future work - Rehearse the panel questions each member is likely to be asked - Confirm every member can explain the part they built | All | TF.3, TF.4 | Whole team | Sep 21 | Sep 23 | N/A (preparation task) | Defence notes | Every member can explain the system, its method, and its limits without notes. | Not started

## Product_Backlog
Story ID | Epic | As a... | I want... | So that... | Acceptance Criteria | Priority | Dependencies | Story Points | Note
US-1.1 | E1 - Staff Authentication & Roles | Agency admin | sign in with one staff account | I reach the tools my role allows | - One sign-in for all staff - Role decides which product opens - Role enforced on the API, not only the UI | Must | - | 3
US-1.2 | E1 - Staff Authentication & Roles | conductor | sign in with credentials issued by my operator | I can report on the trips assigned to me | - Conductors do not self-register - A conductor sees only their own trips | Must | US-1.1 | 3
US-1.3 | E1 - Staff Authentication & Roles | system | create the first admin only while no account exists | a new deployment can be set up but never hijacked later | - Setup endpoint open only on an empty system - Refuses forever after the first admin | Must | US-1.1 | 2
US-1.4 | E1 - Staff Authentication & Roles | staff user | recover my password without an administrator | I am not locked out of my own account | - Reset path for staff accounts - Sign-in attempts are rate limited | Should | US-1.1 | 3 | Sprint 3
US-1.5 | E1 - Staff Authentication & Roles | system | refuse cross-role access on every endpoint | a conductor can never reach operator data | - Automated test in both directions - No passenger endpoint exposes staff identity | Must | US-1.1 | 3
US-2.1 | E2 - Checkpoints & Routes | operator | record every place a bus actually stops | passengers are directed to a real curb, not a city hall | - Name, area, type and terminal flag - Placed on a map with real coordinates | Must | US-1.1 | 3
US-2.2 | E2 - Checkpoints & Routes | operator | distinguish a boarding stop from a timing point | only places people can wait get their own board | - Station gets a public board - Landmark is timing only, never stood at | Must | US-2.1 | 2
US-2.3 | E2 - Checkpoints & Routes | operator | build a route as an ordered list of stops | the system knows the shape of the journey | - Add, remove and reorder stops - Origin baseline forced to zero | Must | US-2.1 | 5
US-2.4 | E2 - Checkpoints & Routes | operator | record how long each leg normally takes | the system has a yardstick to measure against | - Baseline minutes per leg from the previous stop - Editable at any time | Must | US-2.3 | 3
US-2.5 | E2 - Checkpoints & Routes | operator | have travel times measured for me | I do not have to guess a number I cannot know | - Measured from a routing provider - Typical time, not free-flow - Every value returned editable | Should | US-2.4 | 5
US-3.1 | E3 - Fleet & Trips | operator | register the buses in my fleet | trips can be assigned to a real vehicle | - Plate number and operator name - Create, edit, deactivate | Must | US-1.1 | 2
US-3.2 | E3 - Fleet & Trips | operator | create conductor accounts | the people on the road can report | - Admin-created only - Listed and manageable from the console | Must | US-1.1 | 2
US-3.3 | E3 - Fleet & Trips | operator | schedule a trip against a route | passengers can see what is running today | - Route, bus, conductor, scheduled departure - Listed, editable, cancellable | Must | US-2.3, US-3.1, US-3.2 | 3
US-3.4 | E3 - Fleet & Trips | system | freeze the route plan onto each trip | editing a route cannot rewrite a bus already running | - Plan copied at trip creation - Later route edits provably do not affect it | Must | US-3.3 | 3
US-3.5 | E3 - Fleet & Trips | operator | generate trips from a recurring schedule | I do not type every trip by hand | - Schedule by route, time and days - Rolling generation window - One trip can be overridden without breaking the pattern | Must | US-3.3 | 8 | Sprint 3
US-4.1 | E4 - ETA Engine | system | derive how far ahead or behind a trip is | arrival times reflect what is actually happening | - Variance is elapsed time minus cumulative baseline - Measured from departure, never accumulated | Must | US-2.4, US-5.1 | 8
US-4.2 | E4 - ETA Engine | system | re-project every remaining stop on each confirmation | a passenger further down the route gets an updated time | - All later stops shift by the current variance - Confirmed stops keep their observed time | Must | US-4.1 | 5
US-4.3 | E4 - ETA Engine | system | flag an estimate that has gone stale | nobody is shown a confident time nobody can vouch for | - Grace scaled to the segment baseline - Derived on read, never stored | Must | US-4.1 | 3
US-4.4 | E4 - ETA Engine | system | replay trip state from the log stream alone | a late or out-of-order report still settles correctly | - State is a pure replay sorted by report time - No incremental mutation | Must | US-4.1 | 5
US-5.1 | E5 - Conductor Reporting | conductor | confirm reaching a checkpoint in one tap | the system knows where the bus is without any GPS | - One prominent action per screen - No device location read anywhere | Must | US-3.3 | 5
US-5.2 | E5 - Conductor Reporting | conductor | report leaving a stop separately from reaching it | a waiting passenger knows whether to run or settle in | - Reaching and leaving are two events - A timing point takes only one tap | Must | US-5.1 | 3
US-5.3 | E5 - Conductor Reporting | conductor | take back a tap I made by mistake | a wrong button on a moving bus is not permanent | - Five-minute window - Trip recomputes without the removed log | Must | US-5.1 | 3
US-5.4 | E5 - Conductor Reporting | conductor | see the screen respond the moment I tap | I can tell a slow network from a tap that did not register | - Screen advances immediately - Server reply reconciles without a visible jump | Should | US-5.1 | 3
US-6.1 | E6 - Arrivals Board | passenger | see every bus heading to my stop, soonest first | I know what is coming and when | - No account required - Sorted by arrival time | Must | US-4.2 | 5
US-6.2 | E6 - Arrivals Board | passenger | identify the right bus at a busy curb | I board the one I have been waiting for | - Plate number set as an identifier - Route named on every row | Must | US-6.1 | 2
US-6.3 | E6 - Arrivals Board | passenger | know where the bus actually is | I can judge whether the time is believable | - Standing at a stop, or between two named ones - Stale reports marked as such | Must | US-6.1 | 3
US-6.4 | E6 - Arrivals Board | passenger | open one bus and see its whole journey | I can see which stops it has already passed | - Full checkpoint sequence with times - Current position marked | Should | US-6.1 | 3
US-6.5 | E6 - Arrivals Board | passenger | read the wait rather than the clock | I do not have to do arithmetic at a bus stop | - Countdown is the largest element - Clock time kept beneath it - An overdue unconfirmed bus counts up, not down | Should | US-6.1 | 3
US-7.1 | E7 - Stop Discovery | passenger | find my stop by name or on a map | I can start without knowing the official stop name | - Search by stop or city - All stops drawn on a map | Must | US-2.1 | 3
US-7.2 | E7 - Stop Discovery | passenger | see stops near me | I find the closest place to wait | - Ranked by distance within an honest cap - Says plainly when nothing is near | Should | US-7.1 | 3
US-7.3 | E7 - Stop Discovery | passenger | get walking directions to a stop | I can actually reach the curb | - Distance and walking minutes - Opens in the device map application | Should | US-7.2 | 2
US-8.1 | E8 - Seat Availability | conductor | say how full the bus is without extra work | people down the line know whether to wait | - Three levels only - Rides along with a tap already being made | Should | US-5.1 | 3
US-8.2 | E8 - Seat Availability | passenger | see how full an approaching bus was | I do not wait for a bus that cannot take me | - Always shown with where and when it was judged - A full bus reads as not worth waiting for | Should | US-8.1 | 3
US-9.1 | E9 - Terminal Display | terminal operator | show arrivals on a screen at the terminal | waiting passengers see the board without a phone | - Compact rows readable at distance - Pages automatically when it overflows | Could | US-6.1 | 3
US-10.1 | E10 - Live Traffic | system | account for what the road is doing now | the estimate reflects today, not an average day | - Only segments a bus is about to drive - Cached per segment - Falls back to baselines when unavailable | Should | US-4.2 | 5
US-10.2 | E10 - Live Traffic | operator | distinguish a delayed bus from a busy road | the delay flag means something has gone wrong | - Road conditions recorded per leg driven - Lateness still shown, only the blame moves | Should | US-10.1 | 5
US-10.3 | E10 - Live Traffic | system | use a baseline that varies by time of day | a bus in rush hour is not permanently late | - Baseline per time band - Selected from the scheduled departure - Single-value routes still work | Must | US-10.2 | 5 | Sprint 3
US-11.1 | E11 - Journey Search | passenger | search by where I am going | I do not need to know which stop serves my destination | - Any stop later on the trip counts as a destination - Boarding stop returned as the answer | Must | US-6.1, US-7.1 | 8
US-11.2 | E11 - Journey Search | passenger | be shown only buses I can still catch | I am never sent to a curb the bus has passed | - Already-passed stops excluded - A bus standing at a stop is still offered | Must | US-11.1 | 3
US-12.1 | E12 - Offline Operation | conductor | tap where there is no signal | a dead zone does not lose an hour of reports | - Written to the device before sending - Time stamped at the tap, not at sync | Must | US-5.1 | 5
US-12.2 | E12 - Offline Operation | system | replay a queue that arrives out of order | a scrambled batch still lands on the right state | - Idempotency key per tap - Sorted by report time on replay | Must | US-12.1 | 5
US-12.3 | E12 - Offline Operation | operator | correct a trip record after the undo window | a mistake from an hour ago can still be put right | - Admin can view and correct the log stream - Trip recomputes after correction | Must | US-12.2 | 5 | Sprint 3
US-12.4 | E12 - Offline Operation | conductor | open the app with no signal at all | a reload in a dead zone does not strand me | - Application shell cached - Last known trip shown, marked as such | Should | US-12.1 | 5 | Sprint 3
US-12.5 | E12 - Offline Operation | operator | rebuild the system from an empty database | a failure is recoverable | - First admin creatable on an empty system - Trip reconstructable from logs alone | Should | US-1.3 | 3 | Sprint 4
US-13.1 | E13 - Quality | user | use the system on my own phone | the product works where it is actually used | - No screen overflows at phone width - Tested on real devices on mobile data | Must | US-6.1 | 5
US-13.2 | E13 - Quality | system | stay fast with a full week of trips loaded | the board does not slow as the operator grows | - Response times measured and recorded - Passenger reads never call a paid provider | Should | US-13.1 | 3 | Sprint 4

## Testing_Checklist
Category | Test Item
Unit Testing (throughout every sprint) | ETA variance calculation, measured from departure rather than accumulated
Unit Testing (throughout every sprint) | Re-projection of remaining stops after a confirmation
Unit Testing (throughout every sprint) | Cumulative baseline summation across a route
Unit Testing (throughout every sprint) | Skipped checkpoint handling without corrupting the arithmetic
Unit Testing (throughout every sprint) | Out-of-order and duplicate log replay
Unit Testing (throughout every sprint) | Staleness threshold scaled to the segment baseline
Unit Testing (throughout every sprint) | At-stop versus on-the-road position, including the dwell grace
Unit Testing (throughout every sprint) | Traffic applied forward only, never onto a measured variance
Unit Testing (throughout every sprint) | Delay classification with and without recorded road conditions
Unit Testing (throughout every sprint) | Seat report cleared when the bus reaches a new stop
Unit Testing (throughout every sprint) | Client-side locating: a coarse fix never replaces a better one
Unit Testing (throughout every sprint) | Optimistic conductor state transitions
Integration Testing | API and database read/write paths against an in-memory database
Integration Testing | Trip recompute after a log is appended, removed or corrected
Integration Testing | Offline queue drained out of order, including a duplicate
Integration Testing | Traffic provider integration, including the provider being absent
Integration Testing | Automatic travel-time measurement endpoint
Feature Testing (per sprint, at task close) | Checkpoint and route CRUD
Feature Testing (per sprint, at task close) | Fleet, conductor and admin account management
Feature Testing (per sprint, at task close) | Trip scheduling and the frozen plan
Feature Testing (per sprint, at task close) | Conductor reporting: departure, checkpoint, pull-out, arrival
Feature Testing (per sprint, at task close) | Conductor undo inside and outside the window
Feature Testing (per sprint, at task close) | Public arrivals board: departures, arrivals and just-arrived buses
Feature Testing (per sprint, at task close) | Destination-first journey search, including the wrong direction
Feature Testing (per sprint, at task close) | Stop discovery: search, map and stops near me
Feature Testing (per sprint, at task close) | Terminal display paging with more trips than fit
Security Testing | Role boundary enforced in both directions on every endpoint
Security Testing | A conductor cannot act on a trip that is not theirs
Security Testing | Public endpoints require no token and leak no staff identity
Security Testing | Sign-in rate limiting
Security Testing | No secret present in the repository or the client bundle
Security Testing | No device location is read or stored for any vehicle, anywhere
Device & Network Testing | Conductor flow on at least three real Android phones
Device & Network Testing | Passenger board and journey search on real devices
Device & Network Testing | Every screen at 375px with no overflow or overlap
Device & Network Testing | Behaviour on a slow mobile connection, not office wifi
Device & Network Testing | Tap made with the network disabled, then reconnected
Device & Network Testing | Application reload with no signal (after the service worker lands)
Performance Testing | Board and trip response times with a full week of trips
Performance Testing | Passenger reads confirmed never to trigger a paid provider call
Performance Testing | Database indexes reviewed against the queries actually run
Scenario Testing | Passenger scenario walked end to end: find a stop, read the board, plan a journey
Scenario Testing | Conductor scenario walked end to end: depart, confirm, report seats, undo, arrive
Scenario Testing | Operator scenario walked end to end: checkpoint, route, bus, conductor, trip
Scenario Testing | Full regression after final cleanup
Scenario Testing | Production smoke test across all three roles
Scenario Testing | Every scenario repeated on a phone as well as a desktop
Scenario Testing | Edge cases walked deliberately: a bus that stops reporting, a full bus, a skipped checkpoint, a queued tap

## Documentation_Checklist
Category | Document
Technical | README: what the system is, the stack, and how to run it
Technical | Setup guide: local environment, environment variables, seeding
Technical | Architecture document: client, API, database, traffic provider, deployment shape
Technical | Database / schema document: collections, relationships, and why a trip freezes its plan
Technical | ETA methodology document: the formula, its inputs, and its stated limits
Technical | Traffic provider document: what is called, how often, and the fallback
Technical | Offline and sync document: the queue, idempotency, and replay
Technical | Security / access model document: roles, boundaries, and what is public
Technical | Deployment guide: production configuration, build, deploy, backup and recovery
User | Operator guide: checkpoints, routes, travel times, fleet and trips
User | Conductor guide: reporting, seats, undo, and working without signal
User | Passenger guide: finding a stop, reading the board, planning a journey
Testing | Test plan: scope, approach and environments
Testing | Test cases: feature, security, device and performance matrices
Testing | Test report: results, defects raised, and what was deferred
Academic | Final written report, including future work and stated limitations
Academic | Defence notes: how the ETA is calculated and what happens between checkpoints
Academic | Demo script, with what is shown and what is deliberately not

## Deployment_Checklist
# | Item
1 | Production environment variables set and verified (database, token secret, traffic key)
2 | No secret present anywhere in the repository or the client bundle
3 | Production database provisioned, reachable, and access restricted
4 | Production build created and served by the API as a single service
5 | Public URL reachable and the passenger board loads with no account
6 | Production smoke test passed for all three roles
7 | First-admin setup path confirmed closed on the production instance
8 | Logs and monitoring confirmed reachable
9 | Backup and recovery approach documented and tested once
10 | Traffic provider key configured, with the no-provider fallback confirmed working
11 | Demo data and demo accounts seeded on production
12 | Final code cleanup completed (debug logging, dead code, stale comments)
13 | Final regression passed after cleanup
14 | Demo script dry-run at least twice on the production instance
15 | Fallback prepared in case the network fails during the demonstration

## Risk_Register
ID | Risk | Impact | Likelihood | Mitigation
R1 | The ETA method is the research contribution; if it is not demonstrably accurate the project has no result. | High | Medium | Prove it with unit tests from Sprint 1 and keep the engine a pure function so it can be tested without a database. Record the formula and its limits in writing.
R2 | The system depends entirely on conductors tapping. A conductor who forgets, or refuses, leaves passengers with a stale estimate. | High | Medium-High | Keep the conductor screen to one obvious action. Show staleness honestly rather than hiding it. Test on real phones on mobile data (T4.3).
R3 | Long legs create long blind spots: a bus on a 127-minute leg is unobserved for over two hours. | Medium | High | Add landmark timing points on long legs so the gap is halved. Documented as a known limitation.
R4 | One travel-time baseline per leg cannot describe both midnight and rush hour; measured spread on one leg was 32 versus 39 minutes. | Medium | High | Time-of-day baselines scheduled in Sprint 3 (T3.3). Until then, live traffic absorbs most of the error in the ETA.
R5 | Conductors work in dead zones. Reports lost there would corrupt the trip record. | High | Medium | Offline queue with device-side timestamps and idempotency keys, delivered in Sprint 2 (T2.9). Offline start-up in Sprint 3 (T3.4).
R6 | The traffic provider bills per request and the free tier is finite. | Low-Medium | Medium | Only segments a bus is about to drive are queried, cached per segment, and never on the passenger request path. The interval and lookahead are one-line levers.
R7 | A five-person student team with three weeks to the deadline may not finish every Should and Could item. | Medium | Medium-High | Explicit scope checkpoint in Sprint 5 (T5.3). Musts are complete before any Should is started.
R8 | Documentation left to the last days will be thin, and it is a large part of the assessment. | Medium | Medium (if not managed) | Every task in this plan carries its own documentation line. The pack is completed in Finalization (TF.3), not written from scratch there.
R9 | A demonstration failure on the day undoes the work. | High | Low-Medium | Demo data seeded on production, script written, two timed dry runs, and a prepared fallback if the network fails (TF.4).
R10 | Stops placed by geocoding a town name land at the city hall, where no bus goes. | Medium | Medium | Every checkpoint verified against the real road and placed by hand. Already addressed in Sprint 1 (T1.2).

## Coverage_Audit
Feature Area / Lifecycle Activity | Included? | Covered In Sprint(s)
E1 — Staff Authentication & Roles | YES | Sprint 1, Sprint 3
E2 — Checkpoints & Routes | YES | Sprint 1, Sprint 2
E3 — Fleet & Trips | YES | Sprint 1, Sprint 3
E4 — Checkpoint-Based ETA Engine | YES | Sprint 0, Sprint 1
E5 — Conductor Reporting | YES | Sprint 1, Sprint 2
E6 — Public Arrivals Board | YES | Sprint 1, Sprint 2
E7 — Stop Discovery | YES | Sprint 2
E8 — Seat Availability | YES | Sprint 2
E9 — Terminal Display | YES | Sprint 2
E10 — Live Traffic & Accuracy | YES | Sprint 2, Sprint 3
E11 — Destination-First Journey Search | YES | Sprint 2
E12 — Offline Operation & Data Integrity | YES | Sprint 2, Sprint 3, Sprint 4
E13 — Quality, Performance & Devices | YES | Sprint 2, Sprint 4
Lifecycle — Requirements & backlog | YES | Sprint 0
Lifecycle — Architecture & data model | YES | Sprint 0
Lifecycle — Unit & integration testing | YES | Every sprint
Lifecycle — Security testing | YES | Sprint 4
Lifecycle — Performance testing | YES | Sprint 4
Lifecycle — Real-device testing | YES | Sprint 4
Lifecycle — Regression testing | YES | Sprint 5, Finalization
Lifecycle — Full scenario testing | YES | Finalization
Lifecycle — Deployment | YES | Finalization
Lifecycle — Documentation | YES | Every sprint, completed in Finalization
Lifecycle — Demo & defence preparation | YES | Finalization
OUT OF SCOPE — Passenger accounts or sign-in | NO | Not in scope: the board is deliberately open to all
OUT OF SCOPE — Fare payment or ticketing | NO | Not in scope for this project
OUT OF SCOPE — GPS or device tracking of vehicles | NO | Excluded by design; the whole method exists to avoid it